## Sheet1
Task Description | Due Date Start | Due Date End | Window Duration (working days) | Resource (task in days) | Notes | DUE DATE
P1-Project Setup |  | 2025-05-07 | 3 | 0.15
P2-Booking (Recce) |  | 2025-05-14 | 5 | 0.15 | 2 weeks added as buffer
P2-Booking (Shoot) |  | 2025-06-19 | 10 | 0.15 | 2 weeks added as buffer
P3-Attendance (Recce) |  | 2025-06-04 | 1 | 1
P4-Branding Collection |  | 2025-07-03 | 15 | 0.15
P5-Music Collection |  | 2025-07-15 | 5 | 0.15
P6-MOGRT Check |  | 2025-07-10 | 5 | 0.15
P7-MOGRT Creation |  | 2025-07-15 | 3 | 0.25 | Buffer task added
P8-Spec Collection |  | 2025-06-11 | 5 | 0.25
V1-User Manual Collection |  | 2025-06-18 | 5 | 0.3
V2-Script Creation |  | 2025-06-25 | 5 | 0.9
V3-Script Review (Client/Internal) |  | 2025-07-02 | 5
V5-Scene Planning |  | 2025-07-09 | 5 | 0.9
V6-VO Generation |  | 2025-07-15 | 5 | 0.48
P9-Filming (Shoot)* |  | 2025-07-10 | 0.15 | 1 | per video, rounded up to nearest day
P10-Media Ingestion |  | 2025-07-15 | 3 | 0.15
V7-Edit Prep |  | 2025-07-18 | 3 | 0.48
V8-Video Edit (Quoting) |  | 2025-07-23 | 3 | 0.15
V8-Video Edit (Grading)(Editing) |  | 2025-07-25 | 0.25 | 2 | per video, rounded up to nearest half day
V9-Video Review (Internal) |  | 2025-07-30 | 3 | 0.48
V10-Video Revision (Internal) |  | 2025-08-01 | 2 | 0.45 | Buffer task added
V9-Video Review (Client) |  | 2025-08-08 | 5
V10-Video Revision (Client) |  | 2025-08-12 | 2 | 0.45 | Buffer task added
P11-Client Delivery |  | 2025-08-15 | 3 | 0.15 | Equal to Project Due Date
P12-Completion & Invoicing | 1 week after P11 | 2025-08-22 | 5 | 0.15
10.44
* Also calculated per new/amend video even though project level | [5 empty] | TOTAL DURATION (DAYS) FROM SETUP | 100
[6 empty] | TOTAL DURATION (DAYS) FROM SCRIPT CREATION | 58
All figures based on a 7.5 hour working day | [5 empty] | TOTAL DURATION (DAYS) FROM FILMING | 36
OTHER TASKS NOT PART OF THE PIPELINES
Task Description | Due Date |  | Window Duration (working days) | Resource (per vid/task in days) | Notes
V9-Video Review (Reuse) |  |  | 10 |  | Only if Production Type = Reuse on any vid
P7-MOGRT Creation |  |  | 5 | 0.5 | Only if MOGRT doesn't exist already
P2-Booking (Pickups) |  |  | 5
P9-Filming (Pickups)* |  |  | 0.15 |  | per video, rounded up to nearest day
P10-Media Ingestion (Pickups) |  |  | 2
V7-Edit Prep (Pickups) |  |  | 2
V8-Video Edit (Pickups) |  |  | Adhoc |  | Likely to be added to existing edit
V4-Script Revision (Internal) |  |  | Adhoc |  | per video
V4-Script Revision (Client) |  |  | Adhoc |  | per video
V10-Video Revision (Client) |  |  | Adhoc |  | Depends on rework
V10-Video Revision (Internal) |  |  | Adhoc |  | Depends on rework
New/Amend videos | 6
Reuse videos | 3
Formulas:
Due Date End = WORKDAY([Due Date End, row below],-[Window Duration (working days), row below])
Due Date End = WORKDAY([Due Date End, row below],-ROUNDUP(([Window Duration (working days), row below]*6),0))

## Calc Sheet
Task Description | Due Date
P1-Project Setup
P2-Booking (Recce)
P2-Booking (Shoot)
P3-Attendance (Recce)
P4-Branding Collection
P5-Music Collection
P6-MOGRT Check
P7-MOGRT Creation
P8-Spec Collection
V1-User Manual Collection
V2-Script Creation
V3-Script Review (Internal)
V4-Script Revision (Internal)
V5-Scene Planning
V6-VO Generation
P9-Filming (Shoot)
P10-Media Ingestion
V7-Edit Prep
V8-Video Edit (Quoting)
V8-Video Edit (Grading)(Editing)
V9-Video Review (Internal)
V10-Video Revision (Internal)
V9-Video Review (Client)
V10-Video Revision (Client)
P11-Client Delivery | 0
P12-Completion & Invoicing
New Videos
Amend Videos
Reuse Videos
Project Code
Project Due Date