## Calculator
task_code | task_variant | due_date:start | due_date:end | Window (working days) | Duration (capacity in SmartSuite) | Resource (days) | Resource(per video) | Notes
P1-Project Setup |  | 2025-05-02 | 2025-05-07 | 3 | 1 | 0.15
P2-Booking | (Recce) | 2025-05-07 | 2025-05-21 | 10 | 1 | 0.15 |  | 2 weeks added as buffer
P2-Booking | (Shoot) | 2025-06-11 | 2025-06-25 | 10 | 1 | 0.15 |  | 2 weeks added as buffer
P3-Attendance | (Recce) | 2025-06-04 | 2025-06-05 | 1 | 1 | 1
P4-Branding Collection |  | 2025-06-19 | 2025-07-03 | 10 | 1 | 0.15
P5-Music Collection |  | 2025-07-08 | 2025-07-15 | 5 | 1 | 0.15
P6-MOGRT Check |  | 2025-07-03 | 2025-07-10 | 5 | 1 | 0.15
P7-MOGRT Creation |  | 2025-07-10 | 2025-07-15 | 3 | 1 | 0.25 |  | Buffer task added
P8-Spec Collection |  | 2025-06-05 | 2025-06-12 | 5 | 1 | 0.25
V1-User Manual Collection |  | 2025-06-12 | 2025-06-19 | 5 | 1 | 0.3 | 0.05
V2-Script Creation |  | 2025-06-19 | 2025-06-26 | 5 | 1 | 0.9 | 0.15
V3-Script Review | (Internal) | 2025-06-26 | 2025-07-03 | 5 | 1 | 0.48 | 0.08
V4-Script Revision | (Internal) | 2025-07-03 | 2025-07-08 | 3 | 1 | 0.12 | 0.08 | 25% assumption for revision
V5-Scene Planning |  | 2025-07-08 | 2025-07-15 | 5 | 1 | 0.9 | 0.15
V6-VO Generation |  | 2025-07-08 | 2025-07-15 | 5 | 1 | 0.48 | 0.08
P9-Filming | (Shoot) | 2025-07-09 | 2025-07-10 | 1 | 1 | 1 | 0.15 | per video, rounded up to nearest day
P10-Media Ingestion |  | 2025-07-10 | 2025-07-15 | 3 | 1 | 0.15
V7-Edit Prep |  | 2025-07-15 | 2025-07-18 | 3 | 1 | 0.48 | 0.08
V8-Video Edit | (Quoting) | 2025-07-18 | 2025-07-23 | 3 | 1 | 0.15
V8-Video Edit | (Editing) | 2025-07-23 | 2025-07-25 | 2 | 2 | 2 | 0.25 | per video, rounded up to nearest half day
V9-Video Review | (Internal) | 2025-07-25 | 2025-07-30 | 3 | 1 | 0.48 | 0.08
V10-Video Revision | (Internal) | 2025-07-30 | 2025-08-01 | 2 | 1 | 0.225 | 0.15 | Buffer task added
V9-Video Review | (Client) | 2025-08-01 | 2025-08-08 | 5 | 1 | 0.08
V10-Video Revision | (Client) | 2025-08-08 | 2025-08-12 | 2 | 1 | 0.225 | 0.15 | Buffer task added
P11-Client Delivery |  | 2025-08-12 | 2025-08-15 | 3 | 1 | 0.15 |  | Equal to Project Due Date
P12-Completion & Invoicing |  | 2025-08-15 | 2025-08-22 | 5 | 1 | 0.15
10.67
New Videos | 3
Amend Videos | 3
Reuse Videos | 4
EAV Project Code | EAV007
Project Due Date | 2025-08-15
Formulas:
due_date:start = WORKDAY([due_date:end],-[Window (working days)])
due_date:start = [due_date:end, row above]
due_date:end = WORKDAY([due_date:end, row below],-[Window (working days), row below])
due_date:end = MIN([due_date:start, row below]:C8)